## Sheet1
POA&M Item ID | Vulnerability Description | Description | Security Control Number (NC/NH/NI) | Office/Organization | Security Control Name | Implementation Guidance | Severity | POA&M Status | Scheduled Completion Date | Actual Completion Date | Point of Contact | Resources Required | Remediation Plan | Milestone Description | Milestone Date | Milestone Status | Affected Assets | Comments
POAM-001 | Multi-factor authentication not enforced for all admin accounts | Configure MFA enforcement in identity provider and update admin procedures | IA-2 | Security Team | Identification and Authentication | Enable MFA for all privileged accounts | High | Open | 2024-12-31 |  | John Smith - Security Lead | 2 FTE weeks | Configure MFA enforcement in identity provider and update admin procedures | Configure MFA in identity provider | 2024-11-15 | Pending | Admin Portal | Requires coordination with identity management team
POAM-002 | Audit log retention period insufficient | Increase log retention period from 90 days to 1 year | AU-11 | Compliance Team | Audit Record Retention | Extend log retention to meet FedRAMP requirements | Moderate | Ongoing | 2024-11-30 |  | Jane Doe - Compliance | 1 FTE week + storage costs | Increase log retention period from 90 days to 1 year | Update log retention configuration | 2024-10-30 | Completed | Central Logging System | Storage costs approved by management
POAM-003 | Vulnerability scanning frequency needs improvement | Configure automated weekly vulnerability scans | RA-5 | Security Operations | Vulnerability Scanning | Increase scanning frequency to weekly | Low | Open | 2025-01-15 |  | Mike Johnson - SecOps | 4 hours per week | Configure automated weekly vulnerability scans | Update scanning schedule | 2024-12-01 | Pending | All production systems | Requires approval for additional scanner licenses
POAM-004 | Incident response procedures need annual review | Annual review and update of incident response procedures | IR-1 | Security Team | Incident Response Policy and Procedures | Complete annual review of IR procedures | Moderate | Risk Accepted |  |  | John Smith - Security Lead | 16 hours | Annual review and update of incident response procedures | Schedule annual review meeting | 2024-09-15 | Completed | Incident Response Team | Review completed - procedures current
POAM-005 | Database encryption keys require rotation | Implement automated key rotation for database encryption | SC-12 | Database Team | Cryptographic Key Establishment and Management | Implement automated key rotation | High | Ongoing | 2024-10-31 |  | Sarah Wilson - DBA | 1 FTE week | Implement automated key rotation for database encryption | Test key rotation procedure | 2024-10-15 | Completed | Production Database | Testing completed successfully